## Project schedule
| PackTrack | [5 empty] | Project start: | [7 empty] | 2025-03-01
| Sdra Awameh | Team lead |  |  |  |  | Display week: | [7 empty] | 2
| Rasha Alsaleh | Team Member
| Dalaa saqer | Team Member |  |  |  |  | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-03-03 to 2025-05-25
 | time axis 2025-03-03 to 2025-05-25
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Part 1
| Gantt chart | Sdra | 100% | 2025-03-11 | 2025-03-12 | 2
| problem statement Business case | Rasha | 100% | 2025-03-12 | 2025-03-14
| Project scope and goals | Rasha | 100% | 2025-03-14 | 2025-03-16 | 3
| SDLC Model | Sdra | 100% | 2025-03-15 | 2025-03-17 | 3
| planning & Requirements gathering | Dalaa/Sdra/Rasha | 100% | 2025-03-16 | 2025-03-19
| Functional Requirements | Dalaa | 100% | 2025-03-17 | 2025-03-19 | 3
| UI (mock up) | Rasha | 100% | 2025-03-18 | 2025-03-20
| Use Case Diagram | Dalaa | 100% | 2025-03-19 | 2025-03-22 | 4
Design
| System Architecture | Sdra | 0% | 2025-03-24 | 2025-03-27 | 4
| Class-Diagrams | Dalaa | 0% | 2025-03-28 | 2025-03-31 | 4
| Design patterns | Rasha | 0% | 2025-04-04 | 2025-04-08 | 5
| ER | Sdra | 0% | 2025-04-09 | 2025-04-12 | 4
Implementation &Test
| Codeing | Sdra/Rasha/Dalaa | 0% | 2025-04-14 | 2025-05-01 | 18
| Unit Test | Sdra/Rasha/Dalaa | 0% | 2025-05-02 | 2025-05-12 | 11
Evaluation
| Video | Sdra/Rasha/Dalaa | 0% | 2025-05-13 | 2025-05-16 | 4
| PowerPoint | Sdra/Rasha/Dalaa | 0% | 2025-05-17 | 2025-05-23 | 7
Formulas:
Display week: = [Display week:, row below]